## Slide 1
道
HANZI DOJO
Road to Public Beta
What remains before launch — blockers, keys, content, and the runbook
Status review · August 2026

## Slide 2
BASELINE
The product is built — launch waits on sign-off
204
published stories, every one with cover art, narration and an ending check
4,995
HSK words live across levels 1–6 — audio and example sentences included
10,522
neural audio clips generated — narrator plus character voices
~3,000
unit tests green, plus Playwright e2e and visual-regression gates in CI
Where the beta-hardening milestone stands
14 of 16 hardening phases are underway or done. Security boundaries are enforced in the database, metrics were rebuilt to be honest, trust pages are live, and every release now walks a written checklist backed by screenshot tests. The app is live, stable, and shipping weekly — launch is gated on approvals and content, not engineering risk.
Hanzi Dojo · Road to Public Beta
2

## Slide 3
LAUNCH BLOCKERS
Four gates must clear before a wider beta
Chinese editorial sign-off
The one hard block (phase P9): a qualified Chinese reviewer must certify the 14 grammar-guide topics and the published stories. Tooling and reports are ready — the review itself cannot be self-certified.
Legal & trust pages — final review
Privacy, Terms, Support and Methodology are live but remain owner-reviewed drafts. They must be read and approved before the beta announcement treats them as final.
Real-device verification pass
iOS / Safari audio, offline grade replay, and push reminders are built and unit-tested but have never run on real hardware. One structured pass per the testing doc closes this.
Fresh-account walkthrough
One clean end-to-end run: sign-up → onboarding → first study session → first story → language reset from Profile. Proves the first five minutes a new user will actually see.
Hanzi Dojo · Road to Public Beta
3

## Slide 4
OWNER CONSOLE ACTIONS
An hour of console work unblocks all of this
Azure Speech secrets in GitHub Actions
Two secrets (key + region) unlock the staged re-record of 21 mispronounced words and full slow-word / sentence audio for HSK 3–6. The run is prepared — one click after the secrets exist.
A funded LLM key for story generation
Free tiers are proven insufficient (measured across three overnight runs). A funded key — roughly a dollar or two per level — reopens automatic HSK 3–6 story generation.
Auth domain & sign-up email
Set the Supabase Site URL and redirect allowlist to hanzi-dojo.com, then live-test one real sign-up email (Brevo SMTP is configured; delivery has never been verified to an external inbox).
Google sign-in consent screen
Name the OAuth consent screen “Hanzi Dojo” so Google stops showing the raw project URL at sign-in. Optional follow-up: a custom auth domain removes the last trace.
Retire the two dead CI checks
Disconnect the obsolete Cloudflare “Workers Builds” integrations and switch off the retired GitHub Pages site. Red that means nothing trains everyone to ignore red that matters.
Hanzi Dojo · Road to Public Beta
4

## Slide 5
CONTENT
Strong at HSK 1–2 — upper levels need volume
HSK 3–6 story volume
The single biggest remaining content gap. Learners can reach these levels today; the shelves stay thin until stories arrive.
Two lanes are ready: the hand-authored pipeline works now with no external dependency, and the automatic generator reopens the moment a funded LLM key lands.
Publish the held chapters
Two HSK 3 serials are each missing most of a season (held, written, awaiting an editorial pass); one older season needs a rewrite on one side of its mystery before it can publish.
Eight stories sit under the coverage bar
Published HSK 1–3 stories that use more off-list words than the level allows. Each needs a call: swap words, re-level the story, or accept the reach.
25 HSK 6 words lack example sentences
The last of 4,995. Purely a free-tier quota window — one clean run finishes it.
Re-record 21 corrected words
Their pinyin was fixed in the database; the audio still speaks the old reading. The targeted regeneration is staged behind the Azure secrets (slide 4).
Hanzi Dojo · Road to Public Beta
5

## Slide 6
MILESTONE TRACKER
Beta hardening: 16 phases, one hard block
Chart: 
| Blocked | Pending | Needs review | In progress | Complete
Phases | 1 | 3 | 2 | 8 | 2
The critical path
The only blocked phase is Chinese editorial sign-off (P9) — an external reviewer, not engineering. Everything else can proceed around it.
Two reports await a read
The security-boundary audit (P1) and the metrics-integrity rebuild (P2) are done and documented; they need an owner review to close.
Pending by design
Navigation reassessment, manhua polish, and post-launch differentiation (P5 / P8 / P15) deliberately wait until the release gate is healthy.
Hanzi Dojo · Road to Public Beta
6

## Slide 7
ENGINEERING
Polish before the announcement — and after
Before the beta announcement
Accessibility, mobile & performance passes
The a11y audit is underway; mobile and speed passes close the quality phase (P13).
Auth error-path e2e & share-flow check
Prove the sign-up failure states and the reading-test share flow end to end (P11).
Profile & achievements integrity
Scope every Profile number clearly and audit achievements for determinism (P12).
Healthy to follow after launch
FSRS tuning from real review data
The scheduler ships on library defaults; real logs will let us tune retention properly.
Home bootstrap RPC & bundle diet
Collapse the four-query Home load into one call; load only the active font family.
Automated axe checks in e2e
Continuous accessibility scanning — a new dependency, planned as a follow-up.
Hanzi Dojo · Road to Public Beta
7

## Slide 8
RUNBOOK
Four steps from here to the announcement
1
Clear the gates
Editorial sign-off, legal review, the real-device pass, the fresh-account walkthrough — plus the console keys from slide 4.
2
Walk the release checklist
Every merge already walks it: lint, ~3,000 tests, build, e2e with visual screenshots, docs updated. No exceptions on launch week.
3
Wider-push verification
The pre-announcement list: trust pages final, device pass done, nothing in the milestone still blocked, production watched after each deploy.
4
Announce the beta
The merge itself posts to the community automatically; the invite wave follows once the day-one watch is clean.
Hanzi Dojo · Road to Public Beta
8

## Slide 9
THE GATE, IN ONE LINE
Engineering is not the bottleneck.
Sign-off, keys, and stories are.
Editorial
A Chinese reviewer certifies grammar & stories
Legal
Owner approves the four trust pages
Devices
One real-device pass — audio, offline, push
Keys
Azure + LLM secrets set; auth domain live
Four signatures, then we open the doors.